## Variable Values (hidden)
Tech Assistance Topics
Solar Installation
Finance
Procurement/Requests for Proposals
Policy Design (e.g. Virtual Net Metering)
Solar Market Status
Zoning/Permitting/Planning
Other Item Not Listed (please provide descriptive text in next column)
Degree Types
BS
MS
PhD
Postdoc
Non-Degree Trainee
Reporting Periods |  |  | Allowable Reporting Years
2018-07-01 | 2018-09-30 | 07/01/2018 to 09/30/2018 | 2018
10/1/2018 | 2018-12-31 | 10/01/2018 to 12/31/2018 | 2019
2019-01-01 | 2019-03-31 | 01/01/2019 to 03/31/2019 | 2020
2019-04-01 | 2019-06-30 | 04/01/2019 to 06/30/2019 | 2021
2019-07-01 | 2019-09-30 | 07/01/2019 to 09/30/2019 | 2022
2019-10-01 | 2019-12-31 | 10/01/2019 to 12/31/2019 | 2023
2020-01-01 | 2020-03-31 | 01/01/2020 to 03/31/2020 | 2024
2020-04-01 | 2020-06-30 | 04/01/2020 to 06/30/2020 | 2025
2020-07-01 | 2020-09-30 | 07/01/2020 to 09/30/2020 | 2026
2020-10-01 | 2020-12-31 | 10/01/2020 to 12/31/2020 | 2027
2021-01-01 | 2021-03-31 | 01/01/2021 to 03/31/2021 | 2028
2021-04-01 | 2021-06-30 | 04/01/2021 to 06/30/2021 | 2029
2021-07-01 | 2021-09-30 | 07/01/2021 to 09/30/2021 | 2030
2021-10-01 | 2021-12-31 | 10/01/2021 to 12/31/2021
2022-01-01 | 2022-03-31 | 01/01/2022 to 03/31/2022
2022-04-01 | 2022-06-30 | 04/01/2022 to 06/30/2022
2022-07-01 | 2022-09-30 | 07/01/2022 to 09/30/2022
2022-10-01 | 2022-12-31 | 10/01/2022 to 12/31/2022
2023-01-01 | 2023-03-31 | 01/01/2023 to 03/31/2023
2023-04-01 | 2023-06-30 | 04/01/2023 to 06/30/2023
2023-07-01 | 2023-09-30 | 07/01/2023 to 09/30/2023
2023-10-01 | 2023-12-31 | 10/01/2023 to 12/31/2023
2024-01-01 | 2024-03-31 | 01/01/2024 to 03/31/2024
2024-04-01 | 2024-06-30 | 04/01/2024 to 06/30/2024
2024-07-01 | 2024-09-30 | 07/01/2024 to 09/30/2024
2024-10-01 | 2024-12-31 | 10/01/2024 to 12/31/2024
2025-01-01 | 2025-03-31 | 01/01/2025 to 03/31/2025
2025-04-01 | 2025-06-30 | 04/01/2025 to 06/30/2025
2025-07-01 | 2025-09-30 | 07/01/2025 to 09/30/2025
2025-10-01 | 2025-12-31 | 10/01/2025 to 12/31/2025
2026-01-01 | 2026-03-31 | 01/01/2026 to 03/31/2026
2026-04-01 | 2026-06-30 | 04/01/2026 to 06/30/2026
2026-07-01 | 2026-09-30 | 07/01/2026 to 09/30/2026
2026-10-01 | 2026-12-31 | 10/01/2026 to 12/31/2026
2027-01-01 | 2027-03-31 | 01/01/2027 to 03/31/2027
2027-04-01 | 2027-06-30 | 04/01/2027 to 06/30/2027
2027-07-01 | 2027-09-30 | 07/01/2027 to 09/30/2027
2027-10-01 | 2027-12-31 | 10/01/2027 to 12/31/2027
2028-01-01 | 2028-03-31 | 01/01/2028 to 03/31/2028
2028-04-01 | 2028-06-30 | 04/01/2028 to 06/30/2028
2028-07-01 | 2028-09-30 | 07/01/2028 to 09/30/2028
2028-10-01 | 2028-12-31 | 10/01/2028 to 12/31/2028
2029-01-01 | 2029-03-31 | 01/01/2029 to 03/31/2029
2029-04-01 | 2029-06-30 | 04/01/2029 to 06/30/2029
2029-07-01 | 2029-09-30 | 07/01/2029 to 09/30/2029
2029-10-01 | 2029-12-31 | 10/01/2029 to 12/31/2029
2030-01-01 | 2030-03-31 | 01/01/2030 to 03/31/2030
2030-04-01 | 2030-06-30 | 04/01/2030 to 06/30/2030
2030-07-01 | 2030-09-30 | 07/01/2030 to 09/30/2030

## I. Milestones
Recipient: | Recipient Name |  |  | Performance Rating: The performer should self-rate how they are doing on each milestone
DOE Award # or CPS ID: | DE-EE000XXXX (non-lab) or XXXXX (lab award) |  |  | 1 | Conveys that there are significant technical or schedule issues related to achieving the milestone
|  |  |  | 2 | Conveys that there may be minor technical or schedule issues related to achieving the milestone
|  |  |  | 3 | Conveys that there are no technical or schedule issues related to achieving the milestone
Milestone Schedule |  |  | Milestone Completion Dates
SOPO/TWP Milestone # | Milestone Description | Performer | Original Planned | Revised Planned | Actual | Percent Complete | Progress Notes | Rating
1.1 | Example Milestone | NREL | 2019-06-30 | 2019-09-30 | 2019-09-15 | 0% | This is an example of 1-2 sentences of work that is ongoing towards completion of this milestone | 2

## Milestone Example (hidden)
Recipient: | Recipient Name |  |  |  | Perf Rating: The performer should self-rate how they are doing on each milestone
DOE Award #: | DE-EE000XXXX (non-lab) or XXXXX (lab award) |  |  |  | DOE Rating: DOE will use this column to communicate it's review of each milestone as part of the quarterly review feedback
[5 empty] | 1 | Conveys that there are significant technical or schedule issues related to achieving the milestone
[5 empty] | 2 | Conveys that there may be minor technical or schedule issues related to achieving the milestone
[5 empty] | 3 | Conveys that there are no technical or schedule issues related to achieving the milestone
I. Major Task/Milestone Schedule
SOPO Task # M.S. # | Task Title and Milestone Description | Performer | Task Start Date | Milestone Completion Date |  |  |  | Progress Notes
|  |  |  | Original Planned | Revised Planned | Actual | Percent Complete
1.1 | Heat Exchanger Design and Bench Testing
M1 | Definition of heat exchanger design requirements | Spandex | 2012-09-01 | 2012-12-31 | 2013-02-28 | 2013-02-28 | 100% | Contract delays
M2 | Selection of heat exchanger technology | Spandex |  | 2013-04-30 | 2013-06-30 | 2013-06-30 | 100% | Contract delays
1.2 | Turbomachinery Preliminary Design
M3 | Detailed design of hot gas expander | GenTurbo | 2013-01-01 | 2013-03-31 | 2013-06-30 | 2013-06-30 | 100% | Subcontract signing delays
M4 | Detailed design of the turbo-machinery subsystems | GenTurbo |  | 2013-06-30 | 2013-09-30 | 2013-09-30 | 100% | Subcontract signing delays
M5 | Approved turbo-machinery final drawings by DOE | GenTurbo |  | 2013-09-30 | 2013-10-31 | 2013-10-31 | 100% | Accelerated effort to make up time
1.3 | Test Loop Design
M6 | Specification of test loop components | SERI | 2013-04-01 | 2013-06-30 | 2013-08-31 | 2013-08-31 | 100% | Looked at multiple designs
M7 | Isometric drawings for sCO2 test loop | SERI |  | 2013-10-31 | 2013-11-30 | 2013-11-30 | 100% | Performed optimization study
2.1 | Heat Exchanger (Recuperator) Fabrication
M8 | Fabrication and delivery of compact recuperator | Spandex | 2013-07-01 | 2013-12-31 | 2014-02-28 | ---- | 75% | Almost complete
2.2 | Turbomachinery Fabrication
M9 | Delivery of skid with turbo-expander | GenTurbo | 2013-10-01 | 2014-03-31 | ---- | ---- | 50% | Reviewed vendor list; ordered parts
2.3 | Test Loop Hardware Acquisition
M10 | Working sCO2 test loop and baseline performance measurements | SERI | 2014-01-01 | 2014-06-30 | ---- | ---- | 25% | Test loop assembled
3.1 | Performance Testing
M11 | Transient performance maps for the turbo-expander | SERI | 2014-04-01 | 2014-09-30 | ---- | ---- | 0%
3.2 | Endurance Testing
M12 | Operational data for the sCO2 turbo-expander | SERI | 2014-07-01 | 2014-12-31 | ---- | ---- | 0%
3.3 | Design Optimization
M13 | Revised design drawings and specifications of key components scale-up | GenTurbo | 2014-10-01 | 2015-03-31 | ---- | ---- | 0%
EXAMPLE

## II. Tasks
| Instructions: |  |  |  | Recipient: | Recipient Name
| 1) Enter budgeted amounts (not spending) |  |  | DOE Award # or CPS ID: |  | DE-EE000XXXX (non-lab) or XXXXX (lab award)
2) Only include Federal share
Tasks Overview, Including Funding Per Task
Task Number | Task Title | Task Start Date | Task End Date | % of Task Completed | BP 1 ($) | BP 2 ($) | BP 3 ($) | BP 4 ($) | BP 5 ($) | Task Total ($)
1 | [9 empty] | 0
2 | [9 empty] | 0
3 | [9 empty] | 0
4 | [9 empty] | 0
5 | [9 empty] | 0
6 | [9 empty] | 0
Totals |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## III. Spendplan
|  | Recipient: | Recipient Name |  |  | Reporting period: |  | 10/01/2018 to 12/31/2018 |  | ← Then Here | 2018-12-31
|  | DOE Award # or CPS ID: | DE-EE000XXXX (non-lab) or XXXXX (lab award) |  |  |  |  | Click Here ▲
Instructions:
1) Set the Project Dates: Change the data in cells A12, B12, and C12 to correspond to your project. Use Fiscal Years.
2) Initial Spendplan: Fill out Column E (Federal) and Column H (Costshare) with your planned spending for the entire project. These numbers should never be updated.
3) Reporting Period: Click on cell J1 and then cell K1 to select the reporting period (the past quarter). This will provide a color distinction between actuals and updated plan.
4) Actuals & Updated Plan: Fill out Column F (Federal) and Column I (Costshare) with your actual spending and adjusted future projected spending.
5) Cumulative Share: Column G (Federal) and Column J (Costshare) will automatically populate after data is entered in Columns F and I.
Project Spend Plan |  |  |  | Federal Share |  |  | Recipient Share
|  |  |  | Initial Plan | Actuals & Updated Plan | Cumulative | Initial Plan | Actuals & Updated Plan | Cumulative
Year | Quarter | From | To
2018 | Q4 | 2018-07-01 | 2018-09-30 |  |  | 0 |  |  | 0 |  | 2018-09-30
2019 | Q1 | 2018-10-01 | 2018-12-31 |  |  | 0 |  |  | 0 |  | 2018-12-31
2019 | Q2 | 2019-01-01 | 2019-03-31 |  |  | 0 |  |  | 0 |  | 2019-03-31
2019 | Q3 | 2019-04-01 | 2019-06-30 |  |  | 0 |  |  | 0 |  | 2019-06-30
2019 | Q4 | 2019-07-01 | 2019-09-30 |  |  | 0 |  |  | 0 |  | 2019-09-30
2020 | Q1 | 2019-10-01 | 2019-12-31 |  |  | 0 |  |  | 0 |  | 2019-12-31
2020 | Q2 | 2020-01-01 | 2020-03-31 |  |  | 0 |  |  | 0 |  | 2020-03-31
2020 | Q3 | 2020-04-01 | 2020-06-30 |  |  | 0 |  |  | 0 |  | 2020-06-30
2020 | Q4 | 2020-07-01 | 2020-09-30 |  |  | 0 |  |  | 0 |  | 2020-09-30
2021 | Q1 | 2020-10-01 | 2020-12-31 |  |  | 0 |  |  | 0 |  | 2020-12-31
2021 | Q2 | 2021-01-01 | 2021-03-31 |  |  | 0 |  |  | 0 |  | 2021-03-31
2021 | Q3 | 2021-04-01 | 2021-06-30 |  |  | 0 |  |  | 0 |  | 2021-06-30
Totals |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Updated Federal Spend Plan matches the baseline. |  |  | Updated Recipient Spend Plan matches the baseline.
Formulas:
To = EDATE([From],3)-1
From = EDATE([From, row above],3)

## IV. Subcontracts
| Recipient: | Recipient Name
| DOE Award # or CPS Agreement ID: | DE-EE000XXXX (non-lab) or XXXXX (lab award)
Subcontracts (for entire Project Period)
No | Name | Work Description | Budget Period | Task | Planned Funding | Actual Spending
1 | Sub Recipient Name | Brief Summary of Work | 1 | 1 | 0 | 0

## V. Spending Summary (SF-424a)
|  | Recipient: | Recipient Name
|  | DOE Award #/CPS Agreement ID: | DE-EE000XXXX (non-lab) or XXXXX (lab award)
Spending Summary by Budget Category
| Approved Budget per SF-424A |  |  |  | Actual Expenses
Budget Categories per SF-424a | BP 1 | BP 2 | BP 3 | Total | This Quarter | Cumulative | %
a. Personnel |  |  |  | 0 |  |  | #DIV/0!
b. Fringe Benefits |  |  |  | 0 |  |  | #DIV/0!
c. Travel |  |  |  | 0 |  |  | #DIV/0!
d. Equipment |  |  |  | 0 |  |  | #DIV/0!
e. Supplies |  |  |  | 0 |  |  | #DIV/0!
f. Contractual |  |  |  | 0 |  |  | #DIV/0!
g. Construction |  |  |  | 0 |  |  | #DIV/0!
h. Other |  |  |  | 0 |  |  | #DIV/0!
i. Total Direct Charges | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
j. Indirect Charges | [6 empty] | #DIV/0!
k. Total Charges | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
DOE Share |  |  |  | 0 |  |  | #DIV/0!
Cost Share |  |  |  | 0 |  |  | #DIV/0!
Cost Share Percentage | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!

## VI. Accomplishments
Accomplishments |  | Note: This is a cumulative list of accomplishments related to this award since the project began. Accomplishments made within this quarter should be highlighted in yellow. See the following tab for examples. PLEASE MAKE SURE THAT YOU COPY EXISTING BLANK ROWS AND INSERT THEM TO ADD MORE ACCOMPLISHMENTS! This will ensure that things like drop-down lists are still present in new records. |  |  | Recipient: | Recipient Name
[5 empty] | DOE Award #/CPS Agreement ID: | DE-EE000XXXX (non-lab) or XXXXX (lab award)
A | Peer-Reviewed Journal Articles (include only if manuscript accepted, including Lab-published works/white papers)
| Full Author List (of the format FirstAuthor_FirstName FirstAuthor_LastName; SecondAuthor_FirstName SecondAuthor_LastName; etc.) | "Article Title" | Journal/Lab Name | Volume Number | Issue # | pp. (##-##) | Year | DOI (as URL)
B | Books
| Full Author List (same naming convention as Journal Articles) | Book Title | Edition | Publisher | # pages | Year | DOI, if applicable | ISBN
C | Book Chapters
| Full Author List (same naming convention as Journal Articles) | "Chapter Title", Chapter # in Book Title | Edition | Full List of Editors (same naming convention as Authors) | Publisher | pp. (##-##) | Year | DOI, if applicable | ISBN
D | Edited Volumes
| Full Author List (same naming convention as Journal Articles) | Edited Volume Title | Edition | Volume Number | Publisher | Year | DOI, if applicable | ISBN
E | Conference Publications (include only if accepted by organizer)
| Full Author List (same naming convention as Journal Articles) | "Article Title" | Paper Number | Conference/Proceedings Title | Conference Location | Date (MM/DD/YYYY; First day if multiple days) | CD Rom Volume or Volume, pp. (##-##) | DOI, if applicable | ISBN
F | Conference Presentations
| Full Author List (same naming convention as Journal Articles) | "Paper Title" | Paper Number | Session/Symposium/Conference | Conference Location (of the format City, State_Acronym) | Date (MM/DD/YYYY; First day if multiple days) | DOI, if applicable
G | Students and Others Trained/Supported/Supervised/Graduated (including DOE National Lab awards when applicable)
| Name (of the format First_Name Last_Name) | Trainee Type | From: (Semester-Year) | To: (Semester-Year) | Current Position, Affiliation | % Covered | If Cohort, Headcount of Cohort Trainees | Date of Relevant Thesis Published (if applicable) | Thesis Title (if applicable) | Document URL (if applicable)
H | Patent Applications Filed and Patents Awarded
| Full Inventor List (same naming convention as Journal Articles) | "Patent Title" | Date Application Filed | Patent Application Number | Date Awarded (if applicable) | DOI, if applicable
I | Major Honors, Awards, and other Accomplishments
| Recipient Name (of the format First_Name Last_Name) | Award | Sponsor | Date of Award (MM/DD/YYYY)
J | Private Funding (e.g. Venture Capital, Private Equity, etc.) leveraged by DOE Investment
| Private Capital Partner | Amount of Funding | Date (MM/DD/YYYY)
K | Workshops and Other In-Person Events Held
| Title of Event | Start Date of Event (MM/DD/YYYY) | End Date of Event (MM/DD/YYYY) | Location of Event (City, 2-Letter State Abbreviation, e.g. Cleveland, OH) | Event URL, if applicable | Stakeholder Types Engaged (e.g. Utilities; PUCs; etc.)
L | Partnerships (e.g. CRADA for National Lab work, or projects spun out from this work)
| Partnering Organization | Start Date of Partnership (MM/DD/YYYY) | End Date of Partnership, if applicable (MM/DD/YYYY) | Funds Dedicated to Partnership | Notes on Partner Value Add to the Project
M | Other Noteworthy Products
Describe other products produced to date including data or databases, audio or video products, software, models, educational aids or curricula, instruments or equipment.
N | Technical Assistance (TA) Outputs
| TA Recipient Name (of the format FirstName LastName, e.g. John Smith) | Estimated Total Hours Spent Providing TA | Start Date of TA (MM/DD/YYYY) | End Date of TA (even if same as Start Date; MM/DD/YYYY) | Primary TA Topic | Primary TA Topic Text, if Other selected
O | Websites Created
| URL | Name of Site | Short description of site's purpose | Number of unique visits as of time of reporting (date of reporting in parentheses - update for all new reports) | Date Launched (MM/DD/YYYY) | Date of Expected Discontinuation, if applicable (MM/DD/YYYY)
P | Press/Popular Media Mentions of Project Outputs
| Full Author List (as applicable) (of the format FirstAuthor_FirstName FirstAuthor_LastName; SecondAuthor_FirstName SecondAuthor_LastName; etc.) | Article/Blog/Etc. Title | Media Outlet/Publisher Name | URL of mention | Date Published (MM/DD/YYYY)
Q | Webinars Produced
| Date of Webinar (MM/DD/YYYY) | Time of Webinar (in ET) | Title of Webinar | Attendee Count | List of Attendee Expertises (e.g. solar installer; renewables advocacy; etc.) | URL to Recording and/or Slides